## Sheet1
Republic of the Philippines
Province of Samar
MUNICIPALITY OF STA. RITA
20% COMPONENT OF THE IRA UTILIZATION
For the 3rd Quarter, CY 2019
|  |  |  | Target | Project Status |  | No. of
Program or Project | Location | Total Cost | Date Started | Completion | % of | Total Cost Incurred | Extensions, | Remarks
|  |  |  | Date | Completion | to Date | if any
ECONOMIC SERVICES SECTOR
Debt Servicing | LGU - Sta. Rita | 18870854.83 | 2019-01-01 | 2019-12-31
Construction of Multi-Purpose
Center Brgy. Anibongon | Brgy Anibongon | 4636735 | 2019-01-01 | 2019-12-31 | 100% | 4607651.8 |  | completed
Construction of Multi-Purpose
Center Brgy. Bagolibas | Brgy. Bagolibas | 4636735 | 2019-01-01 | 2019-12-31 | 100% | 4612811.86 |  | completed
Construction of Multi-Purpose
Center Brgy. Cabacungan | Brgy. Cabacungan | 4636735 | 2019-01-01 | 2019-12-31 | 100% | 4609311.95 |  | completed
Other Infrastructure Development
Projects | LGU - Sta. Rita | 904691.37 | 2019-01-01 | 2019-12-31 |  |  |  | On - Going
Total |  | 33685751.2 |  |  |  | 13829775.61
We hereby certify that we have reviewed the contents and hereby attest to veracity and correctness of the data or information
contained in this document.
Prepared by: |  |  |  |  | Noted by:
DOMINGO V. ENCINAS | [5 empty] | JOVEN P. TIU
Municipal Budget Officer | [5 empty] | Local Chief Executive