## Sheet1
Republic of the Philippines
Province of Samar
MUNICIPALITY OF STA. RITA
20% COMPONENT OF THE IRA UTILIZATION
For the 2nd Quarter, CY 2020
|  |  |  | Target | Project Status |  | No. of
Program or Project | Location | Total Cost | Date Started | Completion | % of | Total Cost Incurred | Extensions, | Remarks
|  |  |  | Date | Completion | to Date | if any
ECONOMIC SERVICES SECTOR
Debt Servicing | LGU - Sta. Rita | 18870854.83 | 2020-01-01 | 2020-12-31 |  |  |  | On-going
Construction of Multi Purpose | Brgy. Bokinggan | 4636735 | 2020-01-01 | 2020-12-31 | 49% | 2287380.64 |  | On-going
Center @ Barangay Bokinggan
Construction of Multi Purpose | Brgy Gumamela | 4636735 | 2020-01-01 | 2020-12-31 |  |  |  | On-going
Center @ Barangay Gumamela
Construction of Multi Purpose | Brgy. San Isidro | 4636735 | 2020-01-01 | 2020-12-31 |  |  |  | On-going
Center @ Barangay San Isidro
Construction of Multi Purpose | Brgy. Tominamos | 4636735 | 2020-01-01 | 2020-12-31 |  |  |  | On-going
Center @ Barangay Tominamos
Construction of Haning Bridge | Brgy. La Paz | 3500000 | 2020-01-01 | 2020-12-31 |  |  |  | On-going
@ Barangay La Paz
Continuation of Concreting from | Brgy. Alegria | 10000000 | 2020-01-01 | 2020-12-31 |  |  |  | On-going
Nat'l. Highway to Brgy. Alegria
Other Infra Projects | LGU - Sta. Rita | 5500854.83 | 2020-01-01 | 2020-12-31 |  | 92850 |  | On-going
Total |  | 56418649.66 |  |  |  | 2380230.64
We hereby certify that we have reviewed the contents and hereby attest to veracity and correctness of the data or information
contained in this document.
Prepared by: |  |  |  |  | Noted by:
DOMINGO V. ENCINAS | [5 empty] | JOVEN P. TIU
Municipal Budget Officer | [5 empty] | Local Chief Executive